## Sheet1
Schedule
Date | Task | Developer | Hours | Status
Day 1 | Add Profile | D1 | 6
| View Profile | D2 | 6
| Update Profile | D3 | 6
| Add Product in cart | D4 | 6
Day 2 | Remove product from cart | D1 | 6
| View Cart | D2 | 6
| Get order of current user | D3 | 6
| New Order | D4 | 6
Day 3 | Place order/Cancel Order | D1 | 6
| Add Product | D2 | 6
| View Product | D3 | 6
| Discounted Product | D4 | 6
Day 4 | Recently Added | D1 | 6
| Delete Product | D2 | 6
| Search Product | D3 | 6
| Update Product | D4 | 6
Day 5 | Get Product List | D1 | 6
| Get Product by category | D2 | 6
| Add Favourite | D3 | 6
| Remove Favourite | D4 | 6
Day 6 | Add to cart | D1 | 6
| View Favourite | D2 | 6
| Add Store | D3 | 6
| View Store | D4 | 6
Day 7 | Update Store | D1 | 6
| Get category list | D2 | 6
| Get package list | D3 | 6
| Get order list | D4 | 6
|  | Total | 200