## Sheet1
BUYER/SELLER
S. No. | Module | Task | API Type | API Url | Data passsed in Api | Efforts | Description
1 | Profile | Add Profile | POST | /profile | Pass profile bean object | 7 | Save User Profile information in database
|  | View Profile | GET | /profile/{id} | Id of current user | 3 | Return information of current user in json
|  | Update Profile | POST | /profile | Pass profile bean object | 4 | Update User's Information of current user and return same in response
2 | Cart | Add Product in cart | POST | /cart | Pass Cart bean object | 5 | Save product in cart in database and return same
|  | Remove product from cart | DELETE | /cart/{id} | Pass Id of a product | 3 | Remove product from cart and return same
|  | View Cart | GET | /cart/{currentUserId} | Pass Id of Current User | 4 | Return product added in cart of current user
3 | Order History | Get order of current user | GET | /order/{currentUserId} | Pass Id of Current User | 5 | Return all order of current user
|  | New Order | GET | /order/{currentUserId}/{status} | Pass current user id and status | 3 | Return all order of current user whose status is ?
|  | Place order | POST | /order | pass order bean object | 3 | Save order in database and return same
|  | Cancel Order | DELETE | /order/{orderId} | Pass order Id | 3 | Delete Order from database and return same
4 | Product | Add Product | POST | /product | Pass product bean object | 4 | Save Product in database and return same
|  | View Product | GET | /product/{id} | Pass Id of a product | 3 | Return single product
|  | Discounted Product | GET | /discounted-product | N/A | 5 | Return top 10 discounted Product
|  | Recently Added | GET | /recently-added | N/A | 3 | Return top 10 Recently added Product
|  | Delete Product | DELETE | /product/{id} | Pass Id of a product | 4 | Delete Product from database and return same
|  | Search Product | GET | /product/name | Pass name of a product | 5 | Search Product from Database and show Product
|  | update Product | POST | /product | Pass product bean object | 5 | Update Product in firebase and return same JSON.
|  | Get Product List | GET | /product-list | NA | 5 | will get searched product on Home Screen
|  | Get Product by category | GET | /product/{categoryId} | Pass category Id | 3 | Return Product of specified category
5 | Favourite | Add Favourite | POST | /favourite | Pass Favourite bean object | 4 | Save product in favourite in database and return same
|  | Remove Favourite | DELETE | /favourite/{id} | Pass Id of a product | 3 | Remove product from favourite and return same
|  | Add to cart | Post | /favourite/{id} | Pass Product into cart | 5 | Product send to cart Screen
|  | View Favourite | GET | /favourite/{currentUserId} | Pass Id of Current User | 3 | Return product added in favourite of current user
6 | Store | Add Store | POST | /store | Pass store bean object | 6 | Save Store information in Database
|  | View Store | GET | /store/{id} | Id of current user(seller) | 4 | Return information of current user in JSON .
|  | Update Store | POST | /store | Pass store bean object | 5 | Update Store's Information of current user and return same in response
7 | Category | Get category list | GET | /category-list | NA | 5 | Return all categories
8 | Order History(seller) | Get package list | GET | /order/package-list | NA | 5 | Return list of all Packages.
|  | Get order list | GET | /order/order-list | NA | 5 | Return list of all orders in a Package
[5 empty] | Bug solving | 18
[5 empty] | Runtime Error | 16
[5 empty] | Total | 156