## Sheet1
Date | Task | Developer | Hours | Status
Saturday, October 31, 2020 | Splash screen UI design and Code | Aman Jain | 6
| Home screen UI design | Ayushi | 6
Monday, Novemver 2, 2020 | Login and Logout screen UI design and Code | Aman Jain | 6
| Home screen show discounted product Code | Ayushi | 6
Tuesday, November 3, 2020 | Create Profile screen UI design and Code | Aman Jain | 6
| Home screen show category Code | Ayushi | 6
Wednesday, Novmber 4, 2020 | Create Profile screen UI design and Code | Aman Jain | 6
| Home screen show recent product Code | Ayushi | 6
Thursday, November 5, 2020 | Setting screen UI design and Code | Aman Jain | 6
| Search Code | Ayushi | 6
Friday, November 6, 2020 | Cart screen UI desing and Code | Aman Jain | 6
| Product screen show product list UI and Code | Ayushi | 6
Saturday, November 7, 2020 | Unit Testing
First Build Release
Monday, November 9, 2020 | Cart screen UI desing and Code | Aman Jain | 6
| Product detail screen UI and Code | Ayushi | 6
Tuesday, November 10, 2020 | Favorite screen UI design and Code | Aman Jain | 6
| Order History screen UI design and Code | Ayushi | 6
Wednesday, November 11, 2020 | Favorite screen UI design and Code | Aman Jain | 6
| Manage Order screen UI design and Code | Ayushi | 6
Thursday, November 12, 2020 | Naviagtion drawer UI design and Code | Aman Jain | 6
| Order Detail screen UI design and Code | Ayushi | 6
Friday, November 13, 2020 |  |  | 6
6
14 -16 | Diwali Holiday
Tuesday, November 17, 2020 to Thursday, November 19, 2020 | Build Timing and Bug Fixing | 48
Friday, November 20, 2020 | Unit Testing
Final Build Release
|  | Total | 180