## Sheet1
User / Buyer
S.NO. | Module | Sub Module | Task | Efforts | Comments
1 | Splash Screen | ~ | UI implementation | 3 | App Logo, name, version
2 | User Login | By Phone / Google | UI implementation | 4 | ~
|  | Verification | UI implementation
3 | Create Profile | Create Profile | UI implementation & saving details in database | 5 | When user login in app first time
4 | Home Screen | Toolbar | UI implementation + Naviagtion Drawer + Cart | 10 | Home, Settings, Shop by Category, Cart, Order History, Manage Orders,Favroites, Logout
|  | Search bar | Search by product name | 5 | Here user can search different products
|  | View Flipper | UI + Show discount offeres | 10 | Show discount products
|  | Categories | UI implementation in grid | 5 | Here user can shop by viewing different categories
|  | Recent Updates | UI + Show new updates | 5 | Show recent updates
|  | Manage Orders | Manage current order | 6 | View and Cancle current order
|  |  | Tarcking order status |  | View current order delivery status
|  | Order History | View previous orders | 5 | View history
|  | View Products | UI + Show different products grid | 5 | On category click uesr will get product
|  | Product Info | Show products information | 4 | Buy now & Add to cart
UI implentation
|  | Wishlist | Show favourites products list | 7 | View, Buy, Remove favorite products
UI implementation
|  | Settings | Update profile | 7 | Update name, address, email / phone.
UI implementaiton
|  | Log out | UI Alert Dialog+ Yes/ NO | 2 | When user click on logout
5 | Cart | ~ | Show products list with quantity & price | 20 | User can buy products
UI implentation in list
|  | Buy | Show products list & bill |  | When user will click on buy
UI implentation + Buttom Sheet
|  | Change Address | Update delivery details |  | Name, Address, Contact number
|  | Choose Delivery Options | Show delivery options |  | Fast (1day) & Normal (3 days)
6 | Bug Solution | ~ | ~ | 20
7 | Build Timing | ~ | ~ | 20
8 | Total Estimation Time in hours |  |  | 143