## Jira task sheet
S.NO. | Date | Developer | Module | Sub Module | Task | Description | Status
1 | 2020-10-31 | Ayushi | Home Screen | UI Design | Home Screen Design | Designing of Home screen
|  | Aman Jain | Splash Screen | UI Desigen & code | Splash screen UI design and Code | When ever user open the app Check user Login or not
2 | Monday, Novemver 2, 2020 | Ayushi | Home Screen | Code | Show Discounted Products | Display discounted products on home screen
|  | Aman Jain | Login / Logout Screen | UI Desigen & Code | Login and Logout screen UI design and Code | User can login into the app User can logout from the app
3 | 2020-11-03 | Ayushi | Home Screen | Code | Show Categories | Display categories on home screen in grid view Whenever user tap on any particular category, user will navigate to Product screen
|  | Aman Jain | Create Profile | UI Design | Create Profile screen UI design | Create Profile UI design
4 | 2020-11-04 | Ayushi | Home Screen | Code | Show Recent Updates | Display recently updated products
|  | Aman Jain | Create Profile | Code & Testing | Create Profile | When ever user login into the app first time
5 | 2020-11-05 | Ayushi | Home Screen | Code | Search Products Code | Search products by there name
|  | Aman Jain | Setting Screen | UI Design & Code | Setting screen UI design and code | User can update there profile
6 | 2020-11-06 | Ayushi | Product Screen | UI Design & Code | Show Products | Display list of products of specific category When user tap on any particular product user will navigate to Product Detail Screen
|  | Aman Jain | Cart Screen | UI Design | Cart Screen UI Desing | Designing of Cart screen
7 | Saturday, November 7, 2020 | Demo
8 | 2020-11-09 | Unit Testing & First Build Release
9 | 2020-11-10 | Ayushi | Product Detail Screen | UI Design And Code | Show Product Description | Dispaly particular product description User can also Buy product and Add product into cart.
|  | Aman Jain | Cart Screen | Code & Testing | Cart screen code or testing | User can increase or decrease the quantity of products and also buy & remove products from the cart
10 | 2020-11-11 | Ayushi | Order History Screen | UI Design And Code | Show Previous Orders | Display list of all previous order When user tap on any individual user will navigate on Order detail screen
|  | Aman Jain | Favorite screen | UI Design | Favorite screen UI Design | Designing of Favorite Screen
11 | 2020-11-12 | Ayushi | Manage Order Screen | UI Design And Code | Show Recent Orders | Display all recent orders User can manage there recent order User can also cancel there order
|  | Aman Jain | Favorite screen | Code & Testing | Favorite screen Coding and Testing | User can add product into cart & remove
12 | Friday, November 13, 2020 | Ayushi | OrderDetail Screen | UI Design And Code | Show Order Details | Dispaly particular order products list with details
|  | Aman Jain | Navigation drawer | UI Design & Code & Testing | Naviagtion drawer code & testing
13 | 14 -16 November 2020 | Diwali Vacation
14 | Tuesday. November 17,2020 | Missing / Pending Task
15 | 18 - 20 November 2020 | Bug Fixing and Unit Testing
16 | Saturday, November 21, 2020 | Demo
17 | Monday, November 23, 2020 | Final Build Release

## Personal work sheet
S.NO. | Date | Developer | Module | Task | Description | Time | Status
1 | 2020-10-31 | Ayushi | Home Screen | UI design of Home Screen | Designing of Home Screen |  | inporgress
2 | Monday, Novemver 2, 2020 | Ayushi | Home Screen | Code of Discounted products | Code display discounted products in view flipper by api call |  | inporgress
3 | 2020-11-03 | Ayushi | Home Screen | Show categories | Show categories on home screen below Discounted products |  | inporgress
4
5
7
8
9
10
11
12
13
14
15
16
17